## 00 - Notes
Cutover Notes
Short description | Detailed description | Status
Prepare for Credentials data loss | After installing Propel v2.2 and because some security changes, all the credentials’ secrets are going to fail. That’s why you will need to save the current credentials before to migrate so they must be set again after the migration. | Done
Deliverables | Prepare the following list of deliverables before to start: - Propel v2.2.0 Production Build. - Node v20.11.1 LTS (node-v20.11.1-x64.msi) - Mongo DB Community Edition v7 (mongodb-windows-x86_64-7.0.7-signed.msi) - Mongo DB tools (mongodb-database-tools-windows-x86_64-100.8.0.zip). - Mongosh 2.2.0 (mongosh-2.2.0-win32-x64) | Done

## 01 - Update STG data
Cutover action description
With this procedure we are going to refresh the data of the current Propel version in Staging with the one from Production. Then we are going to smoke test the env to ensure everything is working properly.
Step# | Short description | Detailed description | Execution Notes | Status
1 | Check STG version | Double check Production and Staging Propel versions are the same |  | Done
2 | Export Prod data | Export all Propel collections from Production database. Please follow the steps described in the section HOW TO EXPORT COLLECTIONS DATA FROM A PROPEL DATABASE of the Cutover Procedures document. |  | Done
3 | Stop Propel Service | In Staging env stop the Propel Service. |  | Done
4 | Drop DB | Drop the current DB as described in HOW TO DROP PROPEL DATABASE of the Cutover Procedures document. |  | Done
5 | Recreate DB | Recreate the current version Propel DB as indicated in HOW TO CREATE PROPEL DATABASE of the Cutover Procedures document. NOTE: Be sure to use the current version of Propel scripts for this task. Also be sure to use the current PropelUser password from the .env file of Propel API installation folder. Otherwise when you restart the Propel service the service is going to fail. |  | Done
6 | Import data | Import the production data into the Staging Database as detailed in HOW TO IMPORT COLLECTIONS TO A PROPEL DATABASE of the Cutover Procedures document. NOTE: Be sure to use the right import script to match current Mongo DB version. |  | Done
7 | Check STG env | Start Propel Service and Propel desktop app and ensure everything is working as expected. |  | Done

## 02 - Staging migration
Cutover action description
Migration of Staging env from Propel v2.1.0 to v2.2.0
Step# | Short description | Detailed description | Execution Notes | Status
1 | Stop Propel Service | Open the services app of the Windows OS and locate the service named Propel. Then right click it and in the context menu select the option "Stop". |  | Done
2 | Upgrade Node.JS | Check the installed version of node .js by executing in a PowerShell console the follwoing command: node --version If current installed version is less than v20.11.1 LTS then open the Add & Remove app and uninstal Node.JS. When uninstall is done, download and install Node.js v20.11.1 LTS. |  | Done
3 | Uninstall Mongo DB v6 | Proceed with the following steps: - Uninstall Mongo DB Tools 100.6.0 - Uninstall Mongo v6.0.2 - Remove the folder: “C:\Program Files\MongoDB” |  | Done
4 | Install Mongo DB v7 | Proceed with the following steps: - Install Mongo v7.0.7 DB engine (mongodb-windows-x86_64-7.0.7-signed.msi), as service. - Install Mongo DB tools (mongodb-database-tools-windows-x86_64-100.8.0.zip). - Change Path to include current Mongo v7 engine: (using “distrib\cutover\modify-mongo-path.ps1”) - Install Mongosh 2.2.0 (mongosh-2.2.0-win32-x64.zip). To do this unzip the folder and copy the unzipped "\bin" folder into "C:\Program Files\MongoDB\Server\7.0\bin" - Test the path changes by opening a PowerSHell console and executing: mongosh –version It must return the value “2.2.0”. Then execute the following: mongod --version It must return "db version v7.0.7" |  | Done
5 | Customize Mongo DB | Proceed with the following steps: - Create the Admin user “DBA” by executing the script “distrib\cutover\create-admin-user.js” with mongosh. To do this open a powershell console in the folder with the script and run: mongosh create-admin-user.js You will be requested for the “DBA” admin user password during the run. - Stop Mongo DB service. - Edit "mongod.cfg" and ensure to have the following settings security: authorization: enabled - Start Mongo DB service. |  | Done
6 | Create Propel DB | Create the new version Propel DB as indicated in HOW TO CREATE PROPEL DATABASE of the Cutover Procedures document. NOTE: Be sure to use the new version of Propel scripts for this task. |  | Done
7 | Import Propel DB data | Import the production data into the Staging Database as detailed in HOW TO IMPORT COLLECTIONS TO A PROPEL DATABASE of the Cutover Procedures document. NOTE: Be sure to use the right import script to match current Mongo DB version. NOTE: Be sure to use the import script for the upgraded Mongo DB version. |  | Done
8 | Deploy Propel new Version | Copy the latest build to the destination server and deploy the new Propel version. After install perform a quick smoke test and if you have issues check first the section MIGRATION KNOWN ISSUES of the Cutover Procedures document. |  | Done
9 | Full regresion test | Run a full regression test. |  | Done