## 00 - Notes
Cutover Notes
Short description | Detailed description | Status
Deliverables | Prepare the following list of deliverables before to start: - Propel v2.3.0 Production Build. - Node v20.16.0 LTS (node-v20.16.0-x64.msi), only if needed. - Mongo DB Community Edition v7 (mongodb-windows-x86_64-7.0.12-signed) only if needed - Mongo DB tools (mongodb-database-tools-windows-x86_64-100.8.0.zip). - Mongosh 2.3.0 (mongosh-2.3.0-win32-x64) | Not Started

## 01 - Update STG data
Cutover action description
With this procedure we are going to refresh the data of the current Propel version in Staging with the one from Production. Then we are going to smoke test the env to ensure everything is working properly.
Step# | Short description | Detailed description | Execution Notes | Status
1 | Check STG version | Double check Production and Staging Propel versions are the same |  | Done
2 | Export Prod data | Export all Propel collections from Production database. Please follow the steps described in the section HOW TO EXPORT COLLECTIONS DATA FROM A PROPEL DATABASE of the Cutover Procedures document. |  | Done
3 | Stop Propel Service | In Staging env stop the Propel Service. |  | Done
4 | Drop DB | Drop the current DB as described in HOW TO DROP PROPEL DATABASE of the Cutover Procedures document. |  | Done
5 | Recreate DB | Recreate the current version Propel DB as indicated in HOW TO CREATE PROPEL DATABASE of the Cutover Procedures document. NOTE: Be sure to use the current PROD version of Propel scripts for this task. Also be sure to use the currently configured PropelUser password in Staging from the .env file of Propel API installation folder. Otherwise when you restart the Propel service the service is going to fail. |  | Done
6 | Import data | Import the production data into the Staging Database as detailed in HOW TO IMPORT COLLECTIONS TO A PROPEL DATABASE of the Cutover Procedures document. NOTE: Be sure to use the right import script to match installed Mongo DB version. |  | Done
7 | Check STG env | Start Propel Service and Propel desktop app and ensure everything is working as expected. |  | Done

## 02 - Staging migration
Cutover action description
Migration of Staging env from Propel v2.1.0 to v2.2.0
Step# | Short description | Detailed description | Execution Notes | Status
1 | Stop Propel Service | Open the services app of the Windows OS and locate the service named Propel. Then right click it and in the context menu select the option "Stop". |  | Done
2 | Verify Mongo and Node versions | Verify the installed versions of Mongo DB and Node.JS and upgrade to the ones in the notes as needed. |  | Done
3 | Deploy Propel new Version | Copy the latest build to the destination server and deploy the new Propel version. After install perform a quick smoke test and if you have issues check first the section MIGRATION KNOWN ISSUES of the Cutover Procedures document. |  | Done
4 | Full regresion test | Run a full regression test. |  | In Progress

## 03 - Production migration
Cutover action description
Migration of PRODUCTION env from Propel v2.1.0 to v2.2.0
Step# | Short description | Detailed description | Execution Notes | Status
1 | Stop Propel Service | Open the services app of the Windows OS and locate the service named Propel. Then right click it and in the context menu select the option "Stop". |  | Not Started
2 | Production DB backup | Export all Propel collections from Production database. Please follow the steps described in the section HOW TO EXPORT COLLECTIONS DATA FROM A PROPEL DATABASE of the Cutover Procedures document. |  | Not Started
3 | Verify Mongo and Node versions | Verify the installed versions of Mongo DB and Node.JS and upgrade to the ones in the notes as needed. |  | Not Started
4 | Deploy Propel new Version | Copy the latest build to the destination server and deploy the new Propel version. After install perform a quick smoke test and recall to restablish the lost data for Credentials as detailed in the first step of this guide. |  | Not Started
5 | Proceed with Smoke test | Smoke test main functionality. In this case also take care of the new System jobs, (usage and workflow schedules). |  | Not Started